## Sheet1
Risk Matrix
|  | ACCEPTABLE | TOLERABLE | DIFFICULT | UNIDEAL | DISASTROUS
¦ | IMPROBABLE | 1 | 2 | 3 | 4 | 5
¦ | NOT POSSIBLE | 2 | 4 | 6 | 8 | 10
¦ | POSSIBLE | 3 | 6 | 9 | 12 | 15
V | PROBABLE | 4 | 8 | 12 | 16 | 20
| WILL HAPPEN | 5 | 10 | 15 | 20 | 25
| RATING KEY |  |  | LIKELIHOOD KEY |  |  | SEVERITY KEY
| 1 | Ok to continue |  | IMPROBABLE | Risk won't happen |  | ACCEPTABLE | Little to no effect on project
| 6 | Ok but be careful |  | NOT POSSIBLE | Risk unlikely to occur |  | TOLERABLE | Some effects are felt, but nothing minor
| 11 | Proceed with caution |  | POSSIBLE | Risk could potentially occur |  | DIFFICULT | Most effects are felt, fairly major
| 16 | Seek support before continuing |  | PROBABLE | Risk very likely to occur |  | UNIDEAL | Serious impact on project
| 21 | Stop the project |  | WILL HAPPEN | Risk will happen |  | DISASTROUS | Can/Will result in disaster
| Risk | Statement | Response | Objective | Likelihood | Severity | Risk Level
| Mental fatigue | Working on the computer is exhausting, especially for long periods of time | Take 10 - 15 mins max break and step away from computer. Get coffee, stretch legs, etc | Get a good night sleep during the week while working on the project. Avoid working too late/pulling off all nighters | POSSIBLE | ACCEPTABLE to TOLERABLE | 3
| Illness | Getting sick while working on the project (e.g. flu, COVID - 19, etc) | Take painkillers for minor illnesses, isolate from family members if COVID - 19, drink Lemsip for temporary relief | Keeping safe and healthy | NOT POSSIBLE | TOLERABLE to DIFFICULT/UNIDEAL (if COVID - 19 symptoms are serious) | 10 | (If COVID - 19 symptoms are extremely serious, severity would rise to at least 20)
| Gap in knowledge | Not knowing certain practices/topics involved in the project | Look at QA community or online for websites covering topics | Use all available resources (either on the Internet or QA community) | POSSIBLE | TOLERABLE | 6
| Internet slowing | Connection to the Internet drops or stops unexpectedly | Keep pushing work to GitHub to their respective branches. Save work on desktop at the very least | Move closer to Internet source in the house if necessary | PROBABLE | TOLERABLE to DIFFICULT | 12 | (Ranging between 8 and 12)
| Power outage | Sudden power failure in the whole house | *Deep sigh* followed by *rising anger* | Keep computer fully charged and connect to phone hotspot for Internet | IMPROBABLE | DISASTROUS | 20
| Errors/bugs ranging in complexity | Coming across a weird error while coding or pushing stuff via Git | Check on Google for mistakes and try to debug on your own. Worst case scenario, ask trainer for help | Always try to debug yourself until it reaches the extent that you can't do it. Ask in breakout room on Teams or ask trainer for help | POSSIBLE | TOLERABLE to UNIDEAL | 16 | (Ranging between 8 and 16 - the more complex the error, the higher the severity)